## Tabelle1
Preliminary planning of the project
Project name: GESCOPYME
Author: Vadim Budagov
Milestones | Spacec of time | Description | Check: Y/N
1. | 10.02 - 14.02 | Initial Project Setup/Research regarding the project: Joomla, PHP | Yes
2. | 17.02 - 21.02 | Analysis/Preprocessing Data: First Experiments with Data, Joomla and PHP
3. | 24.02 - 28.02 | Requirements and Design: Use-Cases, Classdiagramm …
4. | 02.03 - 03.04 | Development
5. | 06.04 - 17.04 | Development: usability, Layout, possible improvement of logic
6. | 20.04 - 01.05 | Test/ Evaluation and Dokumentation
7. | 04.05 - 08.05 | Review and end of the project
8. |  | Preparation for defense